GÖTÜR Project

[Note: Text enclosed in square brackets and displayed in blue italics (style=InfoBlue) is included to provide guidance to the author and should be deleted before publishing the document.]

# 1. Key milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration start | 24/05/2022 |
| Have some of the core features/use cases for Iteration 4 implemented and tested | 11/06/2022 |
| Iteration stop | 14/06/2022 |

# 2. High-level objectives

* Finalize risk list, work items list and project plan according to given feedback and detected project management issues.
* Finalize glossary, system-wide requirements and use cases and use case model according to given feedback and changed requirements.
* Deliver implemented and end-user documented high business value, core features/use cases, i.e., Register and Return Order processes.

# 3. Work Item assignments

Please see the Work Items List for Work Items to be addressed in this iteration.

# 4. Issues

No issues were encountered during the iteration.

# 5. Evaluation criteria

* Documents are finalized and baselined under revision control.
* All system-level test cases are passed and scenarios are properly tested and demonstrated to key stakeholders for Register and Return Order scenarios.
* End user documentation get favorable acceptance by end users.

# 6. Assessment

|  |  |
| --- | --- |
| Assessment target | Entire Iteration |
| Assessment date | 11/06/2022 |
| Participants | All team members |
| Project status | Green |

## Assessment against objectives

All objectives are achieved in Iteration 4, details of the work items done are as follows;

* Documentations are completed for Iteration 4.
* Register (all roles) and Return Order by User are written in fully dressed format to start implementation.
* Register (all roles) and Return Order by User scenarios are successfully implemented and End User Documentation is completed.
* Test cases for delivered implementations such as Register and Return Order scenarios are written in detail and tests are completed successfully.
* Design Document, Architecture Notebook and Deployment Plan are finalized in accordance to reviews and project plan.
* Manage Personal Information by User, Request Support by User and Manage Users by Administrator scenarios are postponed to next iteration in order to suite iteration timing.

# 7. Iteration Burndown

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| Effort left (hours) | 256 | 236 | 216 | 196 | 180 | 160 | 140 | 120 | 100 | 80 | 60 | 40 | 30 | 20 | 0 |
| Change relative to previous day |  | 20 | 20 | 20 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 20 |